## Sheet1
HOKITIKA
[5 empty] | NLS plan | 76
Date | Action | Ref
15th June 1876 | A site has been selected for the lighthouse, and drawings and specifications have been prepared. In a short time tenders will be called for construction. | AJHR 1876 (Session 1 of 6th Parliament) H - 26 Eleventh Report of the Marine Department for yr ended 30th June 1876. Trans 14th Septmber 1876, McLean (Commissioner of Customs sgn Seed ( Sec of Customs, )appendix A, report by Marine Engineer
30 June 1877 | Nothing more has been done towards the erection of this lighthouse, light originally intended for this place having been transferred to Moeraki. | AJHR 1877 (Session 2 of 6th Parliament) H - 29 Twelth Report of the Marine Department for yr ended 30th June 1877. Trans 5th October 1877, McLean (Commissioner of Customs sgn Seed ( Sec of Customs,) Report from Mr Blackett included in above
10 Jan 1878 | Enclosed I beg leave to hand you a requistion for Harbour Light for Ho Kitika which I have received from the Government of New Zealand, and have to request that you will be good enough to inform me when ready for shipment. | Ac 10706 vol 85, letter Agent - G to Stevenson , 10 Jan 1878 Mckellar (1) incl requistion 205 from Blackett (2)
10 Jan 1878 | Specification for 5th order light notebook | Ac 10706 vol 85, letter Agent - G to Stevenson , 10 Jan 1878 Mckellar (1) incl requistion 205 from Blackett [
11 Jan 1878 | A six feet gun-metal lantern similar to that which you furnished in 1875 for Timaru Lighthouse is required for Ho Kitika (sic) Harbour Light New Zealand. The Lantern to be glazed for half the circle as in Timaru Dormant panes being fitted into the remainder. Please let us know whether you would be willing to supply this lantern at tour former price vizt:-one hundre and eighty three pounds. If so please fill up and send us the accompanying offer. | AC10706 vol 49, pg 71 letter to Dove & Co re New Zealand Lighthouses
11 Jan 1878 | A fifth order Dioptric fixed apparatus for 180 deg and a spherical mirror for 180 deg with pillar and table similar to what you supplied in 1875 for Timaru Lighthouse is required for Ho Kitika (sic) Harbour Light, New Zealand and your price for which was seventy six pounds sterling. Please let us know whether you would be willing to supply the apparatus, pillar & table for Ho Kitika at your former price, and if so please send us an offer in accordance with the annexed for. | Ac 10706 vol 49 pg 72, letter B&F re New Zealand Lighthouses
11 Jan 1878 | We have received your letter of the 10th Instant transmitting a requistion for a harbour light for Ho Kitika which shall have our immediate attention. | Ac 10706 vol 49 pg 73, letter A-G London re New Zealand Lighthouses
12 Jan 1878 | We hereby offer to furnish a 6ft gun metal lantern for Ho Kitika harbour Light in accordance with your plans and specifications for the sum of onehundred and eighty three pounds stg (£183/-/-) and we agree that should any differences arise as to the execution of the work or otherwise, the same shall be left to your decision your award being binding on the contracting parties. The lantern to be delivered within 12 weeks after the date of acceptance of the offer failing which we agree to a deduction being made from the contract price of £5 per week for every week that the contract period is exceeded. | Ac 10706 vol 85, letter Dove to Stevenson , 12 Jan 1878 [186]
Jan 14th 78 | On behalf of the New Zealand Government we hereby accept of your offer of the 12th Instant to supply a lantern for Ho Kitika Light for the sum of one hundred and eighty three pounds sterling | AC10706 vol 49, pg 81 letter to Dove & Co re New Zealand Lighthouses
15 Jan 1878 | We hereby offer to furnish and deliver free in Edinburgh a 5th order fixed light appparatus for 180 deg with spherical mirror 180 deg and pillar & table in accordance with your plan and specification for the sum of seventy six pounds sterling. Ande we agree that should any differences arise as to the execution of the work or otherwise, the same shall be left to your decision your award being binding on the contracting parties. The apparatus etc to be delivered in Edinburgh within 12 weeks after the date of acceptance of the offer failing which we agree to a deduction being made from the contract price of £5 per week for every week that the contract period is exceeded. | Ac 10706 vol 85, letter B&F to Stevenson ,15 Jan 1878 (in English)[187]
17th Janary 1878 | On behalf of the New Zealand Government we hereby accept of your offer to furnish a fifth order fixed apparatus and mirror for Ho Kitika light New Zealand for the sum of seventy six pounds sterling. | Ac 10706 vol 49 pg 95, letter B&F re New Zealand Lighthouses
21 Jan 1878 | We have the honour ? ? Of your letter of the 19th inst informing us of the acceptance of our tender for a fith order apparatus for Ho Kitika, New Zealand. (trans) | Ac 10706 vol 85, letter B&F to Stevenson , 21 Jan 1878 [189]
26 Jan 1878 | The specification for the Ho Kitika apparatus which accompanied your letter of 22 inst indicates 7 upper prisms for the top (coupole) ?? We have never construct a 7th prism in a fixed light apparatus because it become heated and blackened by the lamp. Will you permit us to dispense with the ? (7th prism?) trandslation | Ac 10706 vol 85, letter B&F to Stevenson , 26 Jan 1878 [192]
Janry 30th 78 | We have received your letter of he 26th Instant. The 7th prism may be dispensed with as you propose. | Ac 10706 vol 49 pg 164, letter B&F re New Zealand Lighthouses
27th Febry 1878 | Please furnish along with the fifth order apparatus for Ho Kitika Light New Zealand two fountains aand burners complete, and one stand same as you supplied in 1875 for the fifth order apparartus in Japan. The price to include Doty's patent fee. If you have not retained copies of the Specification & plan of the Japanese lamps please let us know and we shall forward them to you. - The lamps to be fitted to the Hokitika apparatus . When the apparatus and lamps are finished please send them to Messrs Dove & Co Greenside Lane, Edinburgh | Ac 10706 vol 49 pg 164, letter B&F re New Zealand Lighthouses |  | spelling right at las!
1 Mar 1878 | File note 'Offer for Ho Kitika Lamps'.Apparently apparatus for Hokitika completed, Invoice for £9 ( In French) | Ac 10706 vol 85, letter B&F to Stevenson , 1 Mar 1878 [200] | check this.
15 May 1878 | We beg to acquaint you that the Lantern for Hokitika lighthouse is now completed, and the glass fitted in and we shall be glad to have it inspected at your convenience | Ac 10706 vol 85, letter Dove & Co to Stevenson , 15 May 1878 [211]
16 May 1878 | We have finished the 5th order apparatus for Hokitika but have been delayed in sending it due to circumstances beyond our control and we hope to send it next week (translation) | Ac 10706 vol 85, letter B&F to Stevenson , 16 Mar 1878 [212]
5 Juin 1878 | We have the honour to send to you inclosed our invoice, in duplicate, and forms re the Ho Kitiks apparatus which in accordance with your instructions we have today directed carriage paid to Messers Dove at Edinburgh. (Trans) | Ac 10706 vol 85, letter B&F to Stevenson , 16 Mar 1878 [212]
June 13th 78 | We beg to inform you that the lantern for the Ho Kitika Harbour Light is packed and ready for shipment. The packages measure in all about 250 cubic feet and they are addressed to the Secretary of Customs, Wellington | Ac 10706 vol 49 pg 503, letter A-G London re New Zealand Lighthouses
14 June 1878 | be pleased to forward to the EI docks for shipment per 'St. Leonards' for Wellington the Lantern for Ho Kitika Harbour and addressed Secretary of Customs Wgtn New Zealand - Hokitika Light . The vessel sails on the 25th be good enough to forward at once. | Ac 10706 vol 85, memo AG to Stevenson , 14 June 1878 [217]
June 15th 1878 | We have received your letter of the 14th Instant . The HoKitika packages will be forwarded for shipment per "St Leonard". We inclose a detailed list of the contents of the packages and also Messrs Dove's account for the works amounting to £183. | Ac 10706 vol 49 pg 506, letter A-G London re New Zealand Lighthouses
15th June 1878 | Kindly advise us when we may expect lantern to arrive in London for shipment per "St Leonards" for Wellington mentioned in the Agent General for New Zealand's letter of 14th inst? | Ac 10706 vol 85, letter Smith M to Stevenson [218]
June 15th 1878 | We have a letter from the Agent general for New Zealand in which he says that the Ho Kitika lantern packages should be sent to Londond for shipment per "St Leonards" East India Docks London. The packages ahd better go by the Steamer from Granton on Wednesday next as the "St Leonards" sails on the 25th Instant. P S The packages should be sent to the order of MMessrs Smith Morrison & Cp, 117 Leadenhall St London. | AC10706 vol 49, pg 507 letter to Dove & Co re New Zealand Lighthouses
June 17th 1878 | The packages containing the lantern for Ho Kitika light will be sent to your order by Steamer from Granton on Wednesday the 19th inst per list of contents inclosed. The value is £183 but the Agent General will give you directions as to the insurance and freight, | Ac 10706 vol 49 pg 509, letter Smith Morrison & Co London re New Zealand Lighthouses
18th June 1878 | The lightroom stores ordered have been sent off for shipment per "St Leonards" per list of contents of the packages inclosed which also contain the fountains etc for Nugget Point Lighthouse. Thye lantern for Ho Kitika light also goes per the "St Leonards" as per list inclosed. The apparatus, machine lamps etc for Cape Saunders Lighthouse have been tried and they are now being packed for shipment. | Ac 10706 vol 49 pg 512, letter William Seed, Secretary of Customs, Wellington re New Zealand Lighthouses
20 July 1878 | We hereby offer to furnish stores for Hokitika Lighthouse for the sum of five pounds fifteen shillings and sixpence sterling stores £5/17/6. Your acceptance of the offer will oblige. | 16 August 1878 | samml supply stores for energency paraffin light
26 July 1878 | On the 14th of June I forwarded you instructions to ship by the "St Leonards" for Wellington the lantern for Hokitika Harbour. Be good enough to inform me when it was sent up.Note on bottom, Was the Lantern sent up with the L'house material for Nugget Point. Be good enough to give the marks of each shipment and numbers as out shipping agent has made no distinction on BIlls of Lading if it was shipped by the same vessel as the Nugget Point material. | Ac 10706 vol 85, letter AG to Stevenson , 26 July 1878
August 14th 78 | The stores for Ho Kitika light are to be addressed Secretary of Customs Wellington New Zealand Hokitika Light No 4. | Ac 10706 vol 85, letter Smiths& Co to Stevenson , 20 July 1878 [223]
15th August 1878 | Referring to our letter of he 18th Jube we send you inclosed detailed list of the contents of the packages containing the apparatus machine lamps stores etc for Cape Saunders Lighthouse which have been shipped per "Timaru". The small apparatus lamps gas burners etc for Hokitika light are now being packed and will be sent on for shipment next week. This completes the whole of your orders for lighthouse material. We hope the packages will reach you safely. | Ac 10706 vol 49 pg 679, letter William Seed, Secretary of Customs, Wellington re New Zealand Lighthouses
August 15th 78 | The packages containing the small apparatus for Hokitika Light are now ready for shipment. They measure in all about 65 feet and are addressed Secretary of Customs Wellington New Zealand Hokitika Light No 1 etc. Please let us know where you wish the boxes sent on to for shipment. | Ac 10706 vol 49 pg 680, letter A-G London re New Zealand Lighthouses
16 August 1878 | In reply to your letter of the 15th Instant I have to request that you will be good enough to forward the containing the small apparatus for Hokitika Lighthouses to the 'Otaki' loading in the SWI Docks for Wellington. | Ac 10706 vol 85, letter AG to Stevenson , 16 August 1878 [227]
Augt 17 78 | The packages containing the stores and glasses for Hokitika to be sent to London to the order of Messrs Smith Morriosn & Co Leadenhall Street London for shipment per "Otaki" South West India Docks London. Please send off your packages on Wednesday by the Steamer from Granton. | Ac 10706 vol 79 pg 687, letter Smiths & Co to Stevenson , 16th Aug 1878
17 August 1878 | Kindly advise when we may expect the Lighthouse material to arrive in London for shipment per Otaki for Wellington mentioned in the Agent General for New Zealand's letter of 16th Inst. | Ac 10706 vol 85, letter Smith M to Stevenson , 17 Aug 1878[228]
Augt 19th 78 | The lighthouse material for shipment per "Otaki" will be sent by the Steamer from Granton on Wenesday the 21st Instant. We inclose a detailed list of the contenbts of the packages. The packages are marked to your order. | Ac 10706 vol 49 pg 689, letter Smith Morrison & Co London re New Zealand Lighthouses
Augt 22nd 78 | The packages containing the apparatus and stores for Hokitika were forwarded to London yesterday for shipment per "Otaki". We inclose a note of the contents of the different packages and we shall forward the contractors accounts in a day or two. | Ac 10706 vol 49 pg 698 letter A-G London re New Zealand Lighthouses
2nd September 1878 | Apparatus for a new local light at Hokitika, for which gas is to be used, has been ordered from England, but advice of its shipment has not yet been received. | AJHR 1878 (Session 3 of 6th Parliament) H - 12 (Thirteenth) Annual Report of the Marine Department Trans 4th September 1878, G Grey (Commissioner of Customs sgn R Johnson ( Officer in Charge,) ( separation Marine department from Customs Dept.)
30th June 1878 | Lantern and apparatus have been ordered from Home, but no advice of their shipment have been received. | Enclosure 1, report of Marine Engineer
Sep 3rd 78 | We send you inclosed the accounts for the shipment per "Otaki" vizt Messrs Barbier & Fenestre £85 Messrs Smiths & Co 5..17..6 Messrs Dove & Co 16..13..4 Total £107..10..10. | Ac 10706 vol 49 pg 726 letter A-G London re New Zealand Lighthouses
10th Sept 1878 | Letter encloses detailed list content "Otaki " shipment and statement of cost Hokitika, Cape Saunders, specification of Cape Saunder for N to M. notebook | Ac 10706 vol 49 pg 748, letter William Seed, Secretary of Customs, Wellington re New Zealand Lighthouses
1st July 1879 | Hokitika Light will be ready for lighting in September; light, being a local light, will be maintained by the Harbour Board. | AJHR 1879 (Session 2 of 7th Parliament) H - 10 (Fourteenth) Annual Report of the Marine Department Trans 23rd September 1879, G Grey (Minister having charge of the Marine Department sgn R Johnson (Secretary,)
30th June 1879 | Tower is now about ready for lantern and apparatus, which have been sent to Hokitika… maintained by Hokitika Harbour Board. | report of Marine Engineer (Blackett) in above
22 Sept'ber 1879 | on Gaol Hill, tower 18 ft in height, timber, painted white; 5th order fixed white, elevated 122 ft asl, eye 15 ft range 16 nm. | N to M, 42 of 1879, Marine Department, Wgtn, 16 August, 1879, G Grey. Gazette
22 Sept 1879 | Hokitika light exhibited 22 Sept 1879, fixed white 5th order gas (dioptric) maintained by Harbour Board | AJHR 1880 Session II, Vol 2, H13 Annual Report Marine Department trans 3rd Aug 1880 H A Atkinson Min in charge Customs Dept report dated 15 July 1880, signed R Johnson Sec. also Report on Lighthouse Works by Marine Engineer (John Blackett) 31 Mar 1880
1913-08-05 | Green light at end old south wall discontinued 1st Sept. Green light at extreme end new wall | Memo Geo Allport, Sec MD Wgtn, BBAO 5544 151a 1913.3128
1924-10-31 | Light last exhibited | Churchman
1925 | Lamp & Fitting removed. | Churchman